## GUIDE
RISK REGISTER GUIDE
Risk Register | List the name of the department/process.
Provide the date of the assessment.
Risk Owner | This is the person that owns the risks, noting that some risks will be escalated to a higher level.
The owner has accountability for ensuring that the risks are being managed. For example, if being done at the activity level it will usually be the activity manager, the process manager for the risk register at the process level or the head of department (HoD)
Date of Last Review & Date of Next Review | Registers are required to be reviewed and updated at least monthly but may need updating more regularly depending on the nature of the risks.
It is recommended the register be reviewed on an ongoing basis and this can be built into existing management/team meetings by ensuring that risk is documented as an agenda
For the initial risk assessment, leave Date of Last Review blank.
Do any risks need to be escalated? | Significant risks shall be formally communicated and escalated up to the next level of management. List the risk numbers of those risks that you have determined need to have oversight at the next level of management as per the Risk Policy.
To whom are they being escalated?
(To be completed after risks have been rated) | List the person to whom your significant risks are being escalated. The risks you identify for escalation will need to be formally communicated to this person and reflected on their risk register.
Although a risk has been escalated, the risk should remain on the register from which it originated (i.e. if an activity-level risk has been escalated up to process/section and then escalated up to department level management, the risk should appear on all three registers).
Are any risks being de-escalated? | Just as significant risks are escalated as described above, risks that the risk owner determines can be managed at the next level of management down can be de-escalated.
To whom are they being de-escalated? | List the risk numbers and person(s) to whom your risks are being de-escalated.
(To be completed after risks have been rated) | De-escalated risks should remain on the register for one review cycle after the risk has been de-escalated.
Risk Ratings and Treatments Approved by | The approver will often be the risk owner, however if treatments involve a higher level of delegation or oversight, then the risk register may need to be approved by a higher level of management.
Objectives | What are you hoping to achieve? What is the departments objectives
Objectives should be clear and concise. Refer to the Strategic plan/ Corporate Business Plan which outlines the Company's mission and vision and details of the Strategic pillars,goals and objectives.
Risk Number | Assigning a number to each of your risks allows for easier tracking and reporting.
Risk | Risks are the things that can prevent, impede or delay the achievement of each of your objectives. ISO 31000 also defines Risk as the Uncertainity of Objectives.
Risks are articulated as: the event (what can happen), the source (what can cause the event to happen) and the impact (what will happen if the event occurs).
Existing Controls | Controls are processes, procedures and policies that are fully implemented that help control the risk.
Risk rating with existing controls in place | Using the Risk Matrix, rate the risk taking into consideration the strength of the controls that are fully implemented.
This risk rating should be reviewed as treatments become fully implemented (refer to proposed treatments section below).
Is risk rating acceptable? | Are you comfortable with the risk rating you have just determined in consideration of the current controls? If so, select Yes. If you need to do more to bring the risk to a level that the owner is comfortable with, select No.
Sometimes a risk cannot be mitigated further – this may be due to circumstances out of your control (i.e. a change of government) or the cost of proposed treatments may be prohibitive. If so, this should be acknowledged and explained.
Proposed Treatments | If more needs to be done to mitigate risk, list those things that need to be done. Treatments include both actions that are partially implemented and actions that are not yet underway. Once a treatment has been fully implemented, it becomes a control and the risk rating will need to be re-assessed.
Sometimes a risk cannot be mitigated further – this may be due to circumstances out of your control (i.e. a change of government) or the cost of proposed treatments may be prohibitive. If so, this should be acknowledged and explained.
Person Responsible for Implementing Treatments | Identify the person/position responsible for following up and tracking the implementation of the proposed treatments. Be specific: do not identify whole teams.Guidance further exits in the Risk Policy.
Implementation Date for Proposed Treatments | The date should be as specific as possible so that implementation can be followed-up and tracked – avoid using “on-going”. For long term actions, add milestone dates.
Target rating when Proposed Treatments are implemented | This section allows you to make an assessment of how you think the treatments will impact on the risk once all of the proposed treatments identified have been fully implemented. Will they decrease the likelihood and/or the consequence of the risk?
This assessment of a future state helps you think about whether you should do more on top of your currently proposed treatments.

## Summary
Risk Register: xxxxxx Department Risk Register
Head of Department: xxxxxxx
Risk Champion : xxxxxxx
Date of Last review: xxxxxxx
Do any risks need to be escalated?: 0
Are any risks being de-escalated?: 0
Date of Next Review: xxxxxxxxxx
To whom are they being escalated: N/A
To whom are they being de-escalated: N/A
Objectives for the department
1
2
3
4
5
6

## Risk Matrix
Likelihood
| Impact | Rare (1) | Unlikely (2) | Possible (3) | Likely (4) | Almost Certain (5)
Extreme | Catastrophic (5) | Substantial Risk (5) | Substantial Risk (10) | Critical Risk (15) | Severe Risk (20) | Severe Risk (25)
Serious | Major (4) | Moderate Risk (4) | Substantial Risk (8) | Critical Risk (12) | Critical Risk (16) | Severe Risk (20)
Sigificant | Significant (3) | Moderate Risk(3) | Substantial Risk (6) | Substantial Risk (9) | Critical Risk(12) | Critical Risk (15)
Medium | Minor (2) | Tolerable Risk(2) | Moderate Risk (4) | Substantial Risk (6) | Substantial Risk (8) | Substatial Risk (10)
Marginal | Insignificant (1) | Tolerable Risk(1) | Tolerable Risk (2) | Moderate Risk (3) | Moderate Risk (4) | Substantial Risk(5)

## ICT
ICT DEPARTMENT RISK REGISTER 2025/2026
[7 empty] | Risk Assessment - Inherent Risk | [11 empty] | Risk Assessment - Residual Risk | [10 empty] | Risk Response Plan- Residual Risk |  |  | Monitoring and Control
# | Coorporate/Strategic Objective | Department Objective | Process | Risk Description | Root Cause | Potential impact | Probability | Impact | Risk Matrix | [6 empty] | Risk Score | Risk Score description | Existing controls | Probability | Impact | Risk Matrix | [6 empty] | Risk Score | Risk Score description | Response Strategy | Action plan | Opportunities | Raised By | Risk Owner | Status | Risk Category
1 | Strengthen Governance & Compliance | Strengthen Governance & Compliance | 1)Application software acquisition and installation | Non-Compliance to regulatory requirements Forexample UCC and NITA-U requirements | 1) Conflicting government policies and directives | 1) Quality of ICT services are compromised. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1) Appointment of a Data protection officer | Possible | Significant | Impact | C | [5 empty] | 9 | Substantial Risk | Treat (Reduce Risk) | 1) Acquire software platform to track critical compliance details including dates | The ongoing organisational structural review. | MIT | HICT | Open | Operational Risk
|  |  | 2)Change Requests |  | 2) Agencies such as NITA-U and UCC acting as a regulator and service provider. | 2) Legal Penalties and fines |  |  |  | MJ |  |  |  | X |  |  |  | 2) Approved compliance policy and manual |  |  |  | MJ | [8 empty] | 2) Quarterly compliance reporting
|  |  | 3) End user Support |  | 3) Lack of mechanism to track compliance with the relevent legal and regulatory obligations. | 3) Reputational damage 4) Revokation of IPP license |  |  |  | SI | [7 empty] | 3) Periodic reporting to UCC on implemetation status of the PIP license. |  |  |  | SI |  |  | X | [5 empty] | 3)Development of a data protection policy
|  |  | 4) In house software maintenance |  | 4)Lack of a data protection policy |  |  |  |  | MN | [7 empty] | 4) An obligations register is in place to track compliance of the ICT department with the relveant regulatory and legal obligations. |  |  |  | MN | [8 empty] | 4) Conduct a departmental sensitization with the compliance team on the obligations register
|  |  | 5) Outsourced software maintenance | [6 empty] | IN | [7 empty] | 5)An Excel template is in place to track contract and license status, which helps ensure compliance. |  |  |  | IN
|  |  | 6) Access of IT systems. | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
2 | Strengthen Governance & Compliance | Strengthen Governance & Compliance | 1) Allocation of IT equipment | Possibility of redundant and unsued ICT installations or systems. | 1) Inactive ICT Steering Committee | 1) “White-elephant” ICT installations/systems. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1)Approved ICT governance framework. | Unlikely | Minor | Impact | C | [5 empty] | 4 | Moderate Risk | Treat (Reduce Risk) | 1) Rejuvinating the ICT Steering Committee. | Advancement in technology | MIT | HICT | In Progress | Operational Risk
|  |  | 2) Application software acquisition and installation |  | 2) Uncontrolled and decentralized springing up of initiatives and having them funded and executed | 2) Failure to achieve value for money from ICT initiatives. | [11 empty] | 2) Operationalizing the ICT strategy, policies, guidelines, and procedures. | [12 empty] | 2) Training for ICT department staff on contract management
|  |  | 3) IT equipment movement |  | 3) Lack of involvement of key users in development and execution of ICT initiatives. | 3) Lack of management support and ownership | [11 empty] | 3)Change management drives | [12 empty] | 3) Allow only funding and execution of ICT initiatives that have been approved by the steering committee.
|  |  | 4)Change Requests |  | 4) Slow internal processes Vs. highly dynamic technological advancements |  |  |  |  | MJ |  |  |  | X |  |  |  | 4) Include technical training as part of strategic initiative projects |  |  |  | MJ | [8 empty] | 5) Involve stakeholders while building ICT initiatives
[10 empty] | SI | [11 empty] | SI | [8 empty] | 7) More emphasis on change management to prepare staff before new ICT strategic initiatives are deployed
[10 empty] | MN | [11 empty] | MN |  | X | [6 empty] | 8) Utilize the market survey committee productively
[10 empty] | IN | [11 empty] | IN | [8 empty] | 9) Conduct risk assessments for all new ICT initiatives
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
3 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Access of IT systems. | Failure to achieve ICT services availability targets | 1) Inadequate funding for ICT initiatives leading to: | 1) Overall company staff productivity is compromised since most of the day-to-day operations depend on availability of IT services. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1) Semi automated IT Helpdesk is in place for timely logging and resolution of user reported outages and issues. | Possible | Significant | Impact | C | [5 empty] | 9 | Substantial Risk | Treat (Reduce Risk) | 1) Requesting for adequate funding for new IT services and infrastructure. | Management Buy in and support | MIT | HICT | In Progress | Operational Risk
|  |  | 2) End user Support |  | -Insufficient redundancy or failover mechanisms (e.g., lack of high availability configurations) | [12 empty] | 2) Solar winds network monitoring tool is in place | [12 empty] | 2) Training ICT Departmental staff on how to maintain critical services.
[5 empty] | -Inactive or cold data recovery site | [12 empty] | 3) An approved business continuity plan | [12 empty] | 3) Install security monitoring and control tools e.g configure a SOC (Security Operating Center)
[5 empty] | -Inadequate security monitoring and controls | [12 empty] | 4)Routine servicing of ICT equipment and systems. | [12 empty] | 4) stock 10% spares and tools for critical equipment and tools.
[5 empty] | -Lack of spares for some critical equipment | [12 empty] | 5)ICT Policies and Procedures establish governance for change management, incident response, and operations. | [12 empty] | 5) Adopt industry-recommended best practice standard model.
[5 empty] | -Unreliable power supply or cooling systems in data centers or critical ICT sites. |  |  |  |  | MJ |  |  |  | X |  |  |  | 6)Inventory management system was developed in house for asset management which is supposed to flag the aged equipment as per the ICT policy. |  |  |  | MJ | [8 empty] | 6)Complete the upgrade of the ICT Disaster Recovery Site (Secondary Data Centre) at Tororo Substation to a hot recovery site
[5 empty] | 2) Lack of an updated business continuity plan. |  |  |  |  | SI | [11 empty] | SI |  |  | X | [5 empty] | 7)Active technical support contracts and SLAs for all critical systems, hardware and services
[5 empty] | 3)Third party service provider outages (e.g., internet service providers, cloud vendors). |  |  |  |  | MN | [11 empty] | MN | [8 empty] | 8)Service level agreements included in contracts and enforcing penalties
[5 empty] | 4)Aging or inadequate hardware infrastructure (e.g., outdated servers, storage, or network devices) |  |  |  |  | IN | [11 empty] | IN
[5 empty] | 5) Loss of internet services | [5 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
4 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Access of IT systems. | Loss of critical company data | 1) Inadequate data management and security policies. | 1) Reduced staff productivity whose outputs depend on the lost data. | Almost Certain | Catastrophic | Impact | C |  |  |  |  | #NAME? | 25 | Severe Risk | 1)Migration of user data to the cloud that is one drive. | Possible | Major | Impact | C | [5 empty] | 12 | Critical Risk | Treat (Reduce Risk) | 1) Install a real-time security operating centre | Emergence of reliable cloud services ​ | MIT | HICT | In Progress | Operational Risk
|  |  | 2) End user Support |  | 2) Inadequate, untested, backup procedures | 2) System down time | [11 empty] | 2)Implementation of electronic signing of documents | [12 empty] | 2) Organize regular ICT security workshops and daily security tips. | Presence of ICT shared Services such as web hosting, CERT, co-location ​
[5 empty] | 3) Cyber-attacks due to inadequate ICT security tools and controls. | 3) Financial loss | [11 empty] | 3) An approved ICT disaster recovery plan (DRP) | [12 empty] | 3) Review and update of the ICT disaster recovery plan (DRP) | Presence of data centers in Uganda​
[5 empty] | 4) Inadequate ICT security awareness program. | 4) Reputational damage | [11 empty] | 4) Digitization of critical documents residing on hard copies | [12 empty] | 4) Regular review of ICT data management and security policies. | Committed management and board support
[5 empty] | 5) Inadequate funding for data protection and security monitoring tools. | 5) Stakeholder dissatisfaction |  |  |  | MJ | [7 empty] | 5) Use of an Online backup solution - ACRONIS |  |  |  | MJ |  |  | X | [5 empty] | 5) Perform and test backups regularly utilizing the right backup procedures..
[5 empty] | 6) Any other force majure disaster e.g. fire, terorism etc. | 6) Operational Disruption |  |  |  | SI | [7 empty] | 6) Maintaining a cold IT DR site. |  |  |  | SI | [8 empty] | 6)Engage with manufacturers of SDH/DWDM (Hitachi, ZTE, TTC Marconi) equipment to provide updates that close security gaps for intrusion
[5 empty] | 7) Keeping data in hard copy format. |  |  |  |  | MN | [7 empty] | 7) CISCO ASA 5545X firewall in place |  |  |  | MN | [8 empty] | 7)Acquire Network Management Systems (NMSs) for all our SDH & DWDM networks to ensure centralized management which improves detection of intrusions.
[5 empty] | 8) Skills gap |  |  |  |  | IN | [11 empty] | IN | [8 empty] | 8) Increase and approve the budget for security monitoring tools such as Extended Detection and Response (EDR) and Data Loss Prevention (DLP) solutions.
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC |  |  |  | 9). Development of the Data protection policy
[11 empty] | Probability | [11 empty] | Probability | [7 empty] | 10) Development and implmentation of the cybersecurity awareness plan.
5 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Application software acquisition and installation | The possibility that critical business processes remain manual, semi-automated or operating in siloes | 1) Lack of a comprehensive process automation tool (ERP). | 1) Critical business inefficiencies i.e., full of errors, duplications, omissions, and delays e.g., Billing, recruitment, performance mgt. and PAP compensation etc. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1) Existance of standard operating procedures | Possible | Significant | Impact | C | [5 empty] | 9 | Substantial Risk | Treat (Reduce Risk) | 1) Implement an Enterprise Resource Planning (ERP) solution | Advanced technology | MIT | HICT | In Progress | Operational Risk
|  |  | 2)Change Requests |  | 2) Stake holder resistance to change. |  |  |  |  | MJ |  |  |  | X |  |  |  | 2)Deployment of interim automation solutions e.g UETCL connect, Sunsystem, Wayleaves Information System |  |  |  | MJ | [8 empty] | 2) Rigorous change management drives
|  |  | 3) End user Support |  | 3) Limited budget |  |  |  |  | SI | [7 empty] | 3) An approved ICT policy and procedures manual. |  |  |  | SI |  |  | X | [5 empty] | 3) Increase budget provision for ICT.
|  |  | 4) Access of IT systems. |  | 4) Lengthy procurement process Vs technological trend dynamics . |  |  |  |  | MN | [11 empty] | MN | [8 empty] | 4) Adequate training to close skills gaps
|  |  | 5) Allocation of IT equipment |  | 5) Inadequate research and bench marking. |  |  |  |  | IN | [11 empty] | IN | [8 empty] | 5) Mapping of processes company wide 6) Solicit additional funding to support the implementation of more ERP modules.
[5 empty] | 6)Dependancy on legacy systems | [5 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[5 empty] | 7)Deployment of interim automation solutions e.g UETCL connect, Sunsystem, Wayleaves Information System | [5 empty] | Probability | [11 empty] | Probability
6 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Access of IT systems. | Fire outbreaks in ICT facilities | 1) Lack of functional fire suppression services | 1) Loss of revenue | Almost Certain | Catastrophic | Impact | C |  |  |  |  | X | 25 | Severe Risk | 1) Existance of fire supression systems in the Server rooms and battery room. | Unlikely | Significant | Impact | C | [5 empty] | 6 | Substantial Risk | Treat (Reduce Risk) | 1) Review and update the ICT DRP |  | MIT | HICT | In Progress | Operational Risk
|  |  | 2) End user Support |  | 2) Poor maintenance and management of equipment | 2) Reputational damage |  |  |  | MJ | [7 empty] | 2) An approved Safety manual is in place |  |  |  | MJ | [8 empty] | 2) Maintaining functional automatic fire suppression systems in all ICT facilities
|  |  | 3) In house software maintenance |  | 3)No fire drills conducted | 3) Loss of technical equipment |  |  |  | SI | [7 empty] | 3) Fire assembly point is in place |  |  |  | SI |  | X | [6 empty] | 3) Review the established safety measures and standards for fire and related hazards such as electrical faults and gas leaks.
|  |  | 4) IT equipment movement | [6 empty] | MN | [7 empty] | 4) Smoke detectors are installed in all server rooms |  |  |  | MN | [8 empty] | 4) Revamp the current server room fire suppression systems
|  |  | 5) Access of IT systems. | [6 empty] | IN | [7 empty] | 5)Functional industrial air conditioners are installed in all critical ICT facilities |  |  |  | IN | [8 empty] | 5) Install new fire suppression system at the recovery site
|  |  | 6) Allocation of IT equipment | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [10 empty] | Probability
7 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Application software acquisition and installation | Damage/Failure of critical IT equipment | 1) Lack of functional Air conditioners | 1) Quality of ICT services are compromised | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1) Air conditioners are installed especially in the server rooms. | Rare | Major | Impact | C | [5 empty] | 4 | Moderate Risk | Treat (Reduce Risk) | 1. Framework contract for maintenance of Air conditioners for the server room | Management Buy in and support | MIT | HICT | In Progress | Operational Risk
|  |  | 2)Change Requests |  | 2) Lack of a functional UPS | 2) Reduced productivity due to delayed access to IT systems | [11 empty] | 2)Replacement of UPS batteries | [12 empty] | 2. Framework contract for maintenance of UPS
|  |  | 3) End user Support |  | 3) Poor handling habbits of ICT equipment by users | 3) Loss of technical equipment | [11 empty] | 3)Enforcement of ICT policy on handling of equipment | [12 empty] | 3.Soliciting for funds for critical IT spares like switches,firewalls,servers,storage and cctv cameras.
|  |  | 4) In house software maintenance |  | 4) Lack of critical spares |  |  |  |  | MJ |  |  |  | X |  |  |  | 4) Up to date documentation of the ICT network to enable fast restoration in case of failures. |  |  |  | MJ | X | [7 empty] | 4.Quarterly servicing of IT Equipment
|  |  | 5) IT equipment movement |  | 5)Aged equipment |  |  |  |  | SI | [7 empty] | 5)Bi annual servicing of IT Equipment |  |  |  | SI | [8 empty] | 5.Regular monitoring of critical IT equipment.
|  |  | 6) Outsourced software maintenance |  | 6)Inadequate servicing of ICT equipment |  |  |  |  | MN | [7 empty] | For IT: |  |  |  | MN | [8 empty] | 6.Decommisioning devices that have reached end of life
|  |  | 7) Access of IT systems. | [6 empty] | IN | [7 empty] | Documentation of critical IT systems and equipment forexample switches, routers, firewalls configurations, backups, labeling, and critical applications like Sun system, Domain controller, sharepoint, BIS, WIS, Payroll and Billing system |  |  |  | IN
|  |  | 8) Allocation of IT equipment | [7 empty] | RR | UN | PS | LK | AC |  |  | For Telecommunciation |  |  |  |  | RR | UN | PS | LK | AC
[11 empty] | Probability | [6 empty] | Documentation of the telecommunciation network as well as the auxiliary power supplies |  |  |  |  | Probability
8 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Application software acquisition and installation | Cybersecurity breach | 1)inadequate ICT security tools and controls. | 1) Reputation damage | Almost Certain | Catastrophic | Impact | C |  |  |  |  | X | 25 | Severe Risk | 1) Approved SLA's with the service providers | Likely | Catastrophic | Impact | C |  |  |  | X |  | 20 | Severe Risk | Treat (Reduce Risk) | 1)Procurement of next generation firewalls with more advanced features on monitoring the network. | 1)Management Buy in and support | MIT | HICT | In Progress | Strategic Risk
|  |  | 2)Change Requests |  | 2)Inadequate, untested, backup procedures | 2)Operational Disruption | [11 empty] | 2)IT Security officer in place. | [12 empty] | 2) Procurement of an MDR- Managed detection and Response (Crowdstrike MDR) | 2)Government entities to assist in case of a cybersecurity attack (NIRA, ISO etc)
|  |  | 3) End user Support |  | 3)Third party risks | 3)Data Loss or Theft | [11 empty] | 3) Kaspersky End point detection and response (EDR) system in place. | [12 empty] | 2)Develop and implement a Cyber security awareness plan | 3)Advanced firewalls and cyber security systems.
|  |  | 4) In house software maintenance |  | 4)Insufficient user awareness and training | 4)Financial Loss | [11 empty] | 4) CISCO ASA 5545X firewall in place | [12 empty] | 4)Review and update ICT disaster recovery plan (DRP)
|  |  | 5) IT equipment movement |  | 5) Inadequate data management and security policies. |  |  |  |  | MJ | [7 empty] | 5) Use of an Online backup solution - ACRONIS |  |  |  | MJ | [8 empty] | 5)Develop and implement a Data protection policy
|  |  | 6) Outsourced software maintenance | [6 empty] | SI | [7 empty] | 6) Monitoring of the critical systems using Solarwinds application and CACTI for graphing. |  |  |  | SI | [8 empty] | 6) Procurement of a Patch management system
|  |  | 7) Access of IT systems. | [6 empty] | MN | [7 empty] | 7) Restricted access to the UETCL premises and associated substations. |  |  |  | MN | [8 empty] | 7) Implementation of the siem tool
|  |  | 8) Allocation of IT equipment | [6 empty] | IN | [7 empty] | 8) Reviewing user access rights on the system. |  |  |  | IN | [8 empty] | 8) Procurement of a new air gapped backup solution (VERITAS)
[11 empty] | RR | UN | PS | LK | AC |  |  | 9) Carrying out vulnerability assessments bi annually. |  |  |  |  | RR | UN | PS | LK | AC |  |  |  | 9) Testing of the backup procedures
[11 empty] | Probability | [11 empty] | Probability | [7 empty] | 10) Upgrade the ITDR site from a cold site to a warm site.
9 | Strengthen Governance & Compliance | Strengthen Governance & Compliance | 1) Outsourced software maintenance | Violation of service level agreement by Contractors. (Contract risk) | 1) Bureaucracy in the payment approval process | 1) Loss of potential suppliers | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1)Contract and license monitoring template in place. | Rare | Minor | Impact | C | [5 empty] | 2 | Low | Treat (Reduce Risk) | 1)Implementation of the approved SLAs. |  | MIT | HICT | In Progress | Operational Risk
[5 empty] | 2) Delays in contract signing | 2) Reputational damage |  |  |  | MJ |  |  |  | X |  |  |  | 2)Monthly progress procurement reports submitted to CEO |  |  |  | MJ | [8 empty] | 2)ICT policy sensitization workshops
[5 empty] | 3)Lack of an automated contract monitoring tool |  |  |  |  | SI | [7 empty] | 3)Early initiation of procurements. |  |  |  | SI | [8 empty] | 3) Submission of monthly Contract management reports to the Procurement & disposal department.
[10 empty] | MN | [11 empty] | MN | X
[10 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
10 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Application software acquisition and installation | Legacy technology like obsolete or outdated systems | 1) Failure to upgrade or update software | 1) “White-elephant” ICT installations/systems. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1)Patch management | Possible | Significant | Impact | C | [5 empty] | 9 | Substantial Risk | Treat (Reduce Risk) | 1)Engage ERA and justify a request for a budget increament provision for ICT support in critical procurements such as procurement of IT tools for staff like Laptops and computers. |  | MIT | HICT | In Progress | Operational Risk
|  |  | 2)Change Requests |  | 2) Lack of vendor/manufacturer support |  |  |  |  | MJ |  |  |  | X |  |  |  | 2)Vulnerability assessment |  |  |  | MJ | [8 empty] | 2)Deployment of latest or uptodate software
|  |  | 3) End user Support |  | 3) Ever changing technological trends |  |  |  |  | SI | [7 empty] | 3)Daily IT checklists |  |  |  | SI |  |  | X | [5 empty] | 3)Include support component in all critical IT procurements
|  |  | 4) In house software maintenance | [6 empty] | MN | [7 empty] | 4)Daily backup plans |  |  |  | MN | [8 empty] | 4)Keeping abrest with the latest trends in technology through attending conferences, webnars and journals
|  |  | 5) IT equipment movement | [6 empty] | IN | [11 empty] | IN | [8 empty] | 5)Ensure the IT systems have an up to date patches
|  |  | 6) Access of IT systems. | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
|  |  | 7) Allocation of IT equipment | [7 empty] | Probability | [11 empty] | Probability
11 | Improve Operational Efficiency | Improve Operational Efficiency | 1)Application software acquisition and installation | Key man Risk like; | 1) Lack of succession planning | 1)Compromise of quality of IT services | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | 1)Segregation of duties | Unlikely | Significant | Impact | C | [5 empty] | 6 | Substantial Risk | Treat (Reduce Risk) | 1) Review and update the ICT departmental structure. | The ongoing organisational structural review. | MIT | HICT | In Progress | Operational Risk
|  |  | 2)Change Requests | Critical procedures being known by a single expert | 2) Limited training opportunies and financial resources | 2)Reduced productivity | [11 empty] | 2)Training at least two IT staff every financial year | [12 empty] | 2) Conducting trainings for the identified replacements of the critical staff.
|  |  | 3) End user Support |  | 3) Highly technical and experienced IT staff turn over |  |  |  |  | MJ |  |  |  | X |  |  |  | 3)Weekly,monthly and quarterly reporting 4)Maintaining an uptodate knowledge base. |  |  |  | MJ
|  |  | 4) In house software maintenance |  | 4) Lack of documentation |  |  |  |  | SI | [7 empty] | 5)Recruiting of technical staff |  |  |  | SI |  | X
|  |  | 5) IT equipment movement | [6 empty] | MN | [7 empty] | 6)Development of a departmental succession plan. |  |  |  | MN
|  |  | 6) Outsourced software maintenance | [6 empty] | IN | [11 empty] | IN
|  |  | 7) Access of IT systems. | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
|  |  | 8) Allocation of IT equipment | [7 empty] | Probability | [11 empty] | Probability
13 | Strengthen Financial performance | Strengthen Financial performance | 1) Enrolling new fiber capacity co-location clients | low or negligible revenues from dark fiber and capacity business. | a) Failure to remodel the fiber and capacity business inorder to adequatey tap into both market segments. | a) Failure to pay ZTE (equipment vendor for capacity business) with the amounts growing due to interest. | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | a) Bench marking has been carried out with GRIDCO to aid with the remodeling of the business | Possible | Major | Impact | C | [5 empty] | 12 | Critical Risk | Treat (Reduce Risk) | 1) Expedite plans to commercialize and earn significant revenues from the fiber and capacity business | Growing ICT business in the country such as installation of new large data centers. | Manager Telecom | HICT | In Progress | Strategic Risk
|  |  | 2) Support to fiber capacity colocation clients. |  | b) Failure to meet SLAs with existing clients due to prolonged restoration times | b) issuance of credit notes, hence loss of revenue |  |  |  | MJ |  |  |  | X |  |  |  | b) Engaged with a commercialization patner (Soliton) to carry out a business case |  |  |  | MJ |  |  | X | [5 empty] | 2) Engage ERA to avail funds for the tower detection system
[5 empty] | c) Vandalism of the line that causes outage on the optical fiber network | c) Reputational damage |  |  |  | SI | [7 empty] | c) appropriate technologies have been identified, budget estimate drawn and submitted to ERA to install a tower monitoring system that will inform security where the vandalism is taking place. |  |  |  | SI | [8 empty] | 3) Convince management to avail imprest to enable fast restoration in case of failures
[5 empty] | d) Expired contracts with fiber clients |  |  |  |  | MN | [7 empty] | d) Ensure timely notification of the legal and commercial departments of the status of the existing contracts |  |  |  | MN
[10 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
14 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Loss of communication links to the substations | a) Lack of a ring network on the fiber infrastructure | 1) Fastrack the implementation of the Mutundwe - Kabulasoke fiber link as ERA is convinced to approve funds for Kabulasoke - Nkonge | Almost Certain | Catastrophic | Impact | C |  |  |  |  | X | 25 | Severe Risk | a) On the eastern leg (Lugogo to Jinja), there is an existing optical fiber ring from which the network can be protected. Furthermore, there is also an existing outer fiber ring for the Jinja - Tororo segment via Karuma | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | Treat (Reduce Risk) | 1) Fastrack the implementation of the Mutundwe - Kabulasoke fiber link as ERA is convinced to approve funds for Kabulasoke - Nkonge | 1. Advanced/Updated technology : The acquisition of up to date SDH/MPLS-TP multiplexers that can carryout seamless switching to the redundant path in case of a failure on the main path. | Manager Telecom | HICT | In Progress | Operational Risk
|  |  | 2) Enrolling new fiber capacity co-location clients |  | b) Lack of sufficient critical spares to ensure fast restoration from failures | 2+G101) Convince ERA to approve all budgets for spares so that we gradullay stock up on spares of critical components by ensuring that we absorb all the funds they have previously approved. |  |  |  | MJ | [7 empty] | b)Spares for the OPGW and ADSS fiber cables were acquired. |  |  |  | MJ |  |  |  | X |  |  |  |  | 2) Engage with ERA to ensure the approval of all budgets for spares of critical components such as charger controllers, optical fiber splice enclosures, ADSS and OPGW cables | 2. competent training institutions that can equip staff with the necessary knowledge and practical expertise
|  |  | 3) Provision of new data Channel |  | c) Lack of adequate man power to manage the grid as it grows | 3) Vigorously Pursue the+F101 |  |  |  | SI | [7 empty] | c) A request for four more engineers (two to each unit) and six more technicians (two to the Access unit and four to the power supplies unit) was made to HR. |  |  |  | SI | [8 empty] | 3) Ensuring that we absorb all the funds that the regulator previously approved.
|  |  | 4) Provision of technical support to Grid Expansion |  | d) Lack of sufficient training to fill the existing skills gaps. | 4) Pursue critical training to fill urgent skills gaps |  |  |  | MN | [11 empty] | MN | [8 empty] | 3) Vigorously Pursue the filling of all vacancies on the existing approved structure for the Telecom section.
|  |  | 5) Scheduled equipment maintenance |  | e) Lack of support from the equipment manufacturers and software/system developers+F101 |  |  |  |  | IN | [11 empty] | IN | [8 empty] | 4) Pursue critical training to fill urgent skills gaps
|  |  | 6) Support to fiber capacity colocation clients. | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
15 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Delayed Commissioning of the telecommunication equipment in new EPC projects; | a) Failure of EPC Contractors to complete the transmission line on time, or commissioning of the substation way ahead of the lines. | a) Equipment failure before handover yet the substation contractor has already demobilized and left | Possible | Significant | Impact | C | [5 empty] | 9 | Substantial Risk | 1) Ensuring that, together with the project management team, the contractor is not paid fully for the substation telecommunication scope of the project until the transmission line scope (optical fiber/PLC) is completed. case in point is the recently completed Tororo - Opuyo transmission line that was part of the Tororo - Opuyo - Lira 132 kV transmission line & substations project. | Unlikely | Significant | Impact | C | [5 empty] | 6 | Substantial Risk | Treat (Reduce Risk) | 1) Ensure 100% acquisition of the wayleaves corridor before the signing of the EPC contract | Good working relationship with the Manufacturers. | Head Project Implementation | Head Project Implementation | In Progress | Operational Risk
|  |  | 2) Enrolling new fiber capacity co-location clients | The telecommunication equipment comprises of a communication media that resides on the transmission line. If the line is not complete, then the telecommunication equiment cannot be commissioned. The equipment can sometimes malfunction and warranty compromised before official handover | b) Wayleaves acquisition causes delays in completion of the transmission line | b) Loss of warranty of the equipment before they are utilized |  |  |  | MJ | [7 empty] | 2) Engage with manufacturers/develpers of the equipment to maintain or extend the warranties |  |  |  | MJ | [10 empty] | Head Corporate Services | Head ICT
|  |  | 3) Provision of new data Channel |  |  | c) Additional expenses on alternative inadequate solutions for the communication links to the stations. |  |  |  | SI |  |  | X | [8 empty] | SI |  | X | [8 empty] | Head ICT
|  |  | 4) Support to fiber capacity colocation clients. | [6 empty] | MN | [11 empty] | MN | [10 empty] | Manager Telecom
[10 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
16 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Power system outage due to a cyber attack; | a) Connection of the telecommunication Network Management Systems (NMS) to the internet. | a) Total shutdown of the power grid, also affecting the region. | Possible | Catastrophic | Impact | C |  |  | X |  |  | 15 | Critical Risk | a) The telecommunication network is islanded from the internet. Secure connections can be created for support from equipment and system manufacturers and developers | Unlikely | Catastrophic | Impact | C |  | X |  |  |  | 10 | Substantial Risk | Treat (Reduce Risk) | 1) Engage with manufacturers of SDH/DWDM equipment to provide updates that close gaps for intrusion | Adavanced Techology to be used in management of the various multiplexer networks centrally through the respective NMSs. This increases efficiency and reliability on the performance of the multiplexer networks | Manager Telecom | HICT | In Progress | Financial Risk
|  |  | 2) Emergency Maintenance | Unauthorized access to the UETCL control system due to hack through the telecommunication system | b) Weak or no passwords for access to the NMS. | b) Ransom requests to regain access to the power network |  |  |  | MJ | [7 empty] | b) Firewalls are installed at boundary connections to neighboring networks |  |  |  | MJ | [8 empty] | 2) Engage with the IT section to support in this area of cyber security. |  | Manager IT
|  |  | 3) Enrolling new fiber capacity co-location clients |  | c) Connection to external networks like neighboring transmission networks without firewalls | c) Severe reputation damage |  |  |  | SI | [7 empty] | c) Strong passwords and tracking implemented on the access to the NMS |  |  |  | SI | [8 empty] | 3) Acquire Network Management Systems for all our Synchronous Digital Hierarchy networks
|  |  | 4) Provision of new data Channel | [6 empty] | MN | [11 empty] | MN
|  |  | 5) Provision of technical support to Grid Expansion | [6 empty] | IN | [11 empty] | IN
|  |  | 6) Scheduled equipment maintenance | [7 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
|  |  | 7) Support to fiber capacity colocation clients. | [7 empty] | Probability | [11 empty] | Probability
17 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Failure of the LVAC/DC systems on the grid. | a) Lack of redundancy on the LVAC/DC busses | a) Failure of the 415/240 VAC, 48VDC and 110VDC busses hence causing the powering down of the protection system on the network hence National or partial blackouts | Possible | Catastrophic | Impact | C |  |  | X |  |  | 15 | Critical Risk | a) Redundancy on the 48VDC and 110VDC busses has been established on approximately 70% of the power grid, offices and premises. | Unlikely | Major | Impact | C | [5 empty] | 8 | Substantial Risk | Treat (Reduce Risk) | 1) Continue to gradually replace the old and dilapidated standby generators, chargers and battery banks with ERA's approval. This year, we plan to replace as follows: | Adavanced Technology e.g. the latest thytronic based chargers that have advanced central management systems that ease operation and maintenance of the LVDC busses | Manager Telecom | HICT | In Progress | Operational Risk
|  |  | 2) Emergency Maintenance |  | b) Lack of monitoring of the alarms or health statusses of the LVAC/DC systems | b) Potential destruction of equipment and loss of life due to fire hazards on the grid |  |  |  | MJ | [7 empty] | b) The health status and alarms of the LVAC/DC busses is now being monitored at NCC |  |  |  | MJ |  | X | [6 empty] | a) Fort portal, Rugonjo and Lugazi standby generators
|  |  | 3) Provision of technical support to Grid Expansion |  | c) Existance of old and dilapidated standby generators, 48, 110VDC chargers and battery banks on the DC busses |  |  |  |  | SI | [7 empty] | c) Sequentially replacing the old and dilapidated standby generators, chargers and battery banks |  |  |  | SI | [8 empty] | b) Hoima, Nkenda, Kampala North, Lugazi Masaka chargers & battery banks
|  |  | 4) Scheduled equipment maintenance | [6 empty] | MN | [7 empty] | d) Continuosly ensure that alarms are installed and functional on the LVAC/DC busses |  |  |  | MN | [8 empty] | 2) Gradually provide redundancy on all the LVDC busses as well as the LVAC for the most critical centers such as control center and major generation plants.
|  |  | 5) Support to fiber capacity colocation clients. | [6 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
18 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Failure of the UETCL telephone system; | a) Failure of the Omni PCX servers that act as the central switches | a) Grid operations shall be severely affected | Possible | Major | Impact | C | [5 empty] | 12 | Critical Risk | a) UETCL has installed two servers, one at Head office and the second at Lugogo. There is a UTeL PSTN interface to the server at Head office and MTN PSTN interface to the server at Lugogo for backup. | Unlikely | Significant | Impact | C | [5 empty] | 6 | Substantial Risk | Treat (Reduce Risk) | 1) In addition to the existing MTN PSTN interfaces, Procurement is underway to add an AIRTEL PSTN interface to the backup server at Lugogo |  | Manager Telecom | HICT | In Progress | Operational Risk
|  |  |  | UETCL operates a telephone network that covers both the grid as well as the corporate segments. Its failure affects business continuity for both the grid and corporate segments. | b) Failure of the Optical fiber connecting Lugogo to Hannington through which the telephone network is extended from Hannington | b) Corporate operations shall be severely affected |  |  |  | MJ |  |  | X | [8 empty] | MJ | [8 empty] | 2) Engage ERA to avail funds for the construction of a better overhead link between Lugogo and Hannington
[5 empty] | c) Failure of the corporate LAN/WAN over which the telephone network is carried |  |  |  |  | SI | [7 empty] | b) On top of the underground Line, Theres a backup overhead fiber link between Hannington and Lugogo via the UEDCL network but it is of bad quality and yet UEDCL is slow to respond when faults occur. Procuremt is underway to install a better one. |  |  |  | SI |  | X
[10 empty] | MN | [11 empty] | MN
[10 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
19 | Improve Operational Efficiency | Improve Operational Efficiency | 1) Provision of voice service | Increased downtime on the communication links due to: | a) Lack of separate Telecom PoPs for the fiber and capacity clients at many of the substations especially the old ones | a) Potential outage on the grid | Likely | Major | Impact | C | [5 empty] | 16 | Critical Risk | a) For some new stations separate PoPs have been constructed whereas for others, the PoP is a separate room on the plant house with access from outside. Depending on the available land for the substation, we can specify one or the other | Unlikely | Significant | Impact | C | [5 empty] | 6 | Substantial Risk | Treat (Reduce Risk) | 1) Engage with planning department to construct separate telecom PoPs or rooms accessible from outside. |  | Manager Telecom | HICT | In Progress | Operational Risk
|  |  | 2) Enrolling new fiber capacity co-location clients |  | b) Lack of effective supervision of the fiber clients as they access their equipment for maintenance | b) Potential destruction to equipment and loss of life of the client equipment |  |  |  | MJ |  |  |  | X |  |  |  | b) Lack of access to the station without approval by the communiation engineers. Access request forms have to be submitted by the clients and approved by UETCL communication engineers. |  |  |  | MJ | [8 empty] | 2) Continue with close supervision of the clients as they access the substations
|  |  | 3) Support to fiber capacity colocation clients. | Fiber clients disrupting operation of the grid during their access to their equipment for maintenance; | [5 empty] | SI | [7 empty] | c) Supervision of the clients by the station attendant during the working hours. |  |  |  | SI |  | X | [6 empty] | 3) Ensure that the UETCL cabinents are kept under lock and key and only accessed by authorised personnel.
|  |  | 4) Communication Equipment Maintenance | Currently, for many of the substations, the optical fiber and capacity clients install their equipment within the plant houses. They could accidentally or itentionally disrupt the operations of the grid | [5 empty] | MN | [7 empty] | d) Engage with planning department (for all future projects) during drawup of technical specifications to construct separate telecom PoPs in the substations, or to have these rooms accessible from outside the plant house. |  |  |  | MN
[10 empty] | IN | [11 empty] | IN
[11 empty] | RR | UN | PS | LK | AC | [7 empty] | RR | UN | PS | LK | AC
[11 empty] | Probability | [11 empty] | Probability
|  |  | Prepared by; | Ocaya Joseph & Kibuuka Yusuf | Reviewed by; Chris Oleke
|  |  | Signature; |  | Signature;