## Files 1
REFERENCES |  |  | PROJECTS AFFECTED PERSON'S DETAILS | [8 empty] | DATA COLLECTION TOOLS | [12 empty] | PAP DISCLOSURE DETAILS | [15 empty] | Comment
NO. | NO. CONSULTANT'S | WIS HH_ID | DISTRICT | SUB - CTY | PARISH | Village/LC1 | PLOT REF. | DES | NAMES OF PAP | CONTACT | NIN | Survey/ Strip Map | Valuation/ Assessment | CGV APPROVED REPORT | Soc Econ Info | STR /Fixture photos | Plot no. | Block no | Location | status | PAP photos | Option Grp (1, 2, 3A,3B) | Initial Date of Disclosure | Disclosing officer | DISCLOSURE STATUS | FEEDBACK | Remarks | STRINGING | ROW (acres) | WL (acres) | TOTAL Acreage | Re-disclosure Date | LAND ASSESSMENT | CROPS ASSESSMENT | FIXTURES ASSESSMENT | TOTAL ASSESSMENT AMOUNT | DISCLOSING OFFICER | Payment Status | Vacation Due Date | DATE OF CAPTURE
1 | 4KMRS-00016 | 74140 | WAKISO | WAKISO | BULOBA | BUKASA-BUKULU | BBKL-AP011-036 | CO1&CO2 | MUGAMBWA NGOZI & ATUSASIIRE ANNAH RURWANA | 0782328484/ 0772611544 |  | YES | YES |  | YES | N/A | 3078 | 314 | MENGO-BUSIRO | Printed | Yes | 2 | 2016-07-14 | Henry K. | DISCLOSED 2 | QUERIED 2 | QUERIED |  | 0 | 0.0095 | 0.0095 | 2019-05-06 | 1850601 | 0 | 0 | 1850601 | Yasir k. | PENDING PAYMENT | 1900-06-28
2 | KW-MSK-0213 | 60892 | MPIGI | KAMENGO | KYANJA | BUGABO | BUGA/AP016/003 | LO | KIZALA YUANA (DECEASED) C/O KABONGE RICHARD | 0705707041 | CM69012103WMJL | yes | yes | FILED | yes |  | 602 | 149 | KAMENGO-MAWOKOTA | Printed | Yes | 2 | 2025-05-05 | SARAH WASIAMA | DISCLOSED 2 | QUERIED 2 | QUERIED | OK | 0.1938 | 1.194 | 1.3878 |  | 3964140 | 0 | 0 | 3964349 | SARAH WASIAMA | PENDING PAYMENT | 1900-06-28 | 2025-05-19
3 | KW-MSK-0511 | 1336 | MPIGI | BUWAMA | MBIZZINNYA | BUWAMA B | BUWA/AP019/007 | T17 | MUSOKE JOSEPH |  |  | yes | yes |  | yes | N/A | N/A | N/A | N/A | Printed | Yes | 2 | 2014-04-14 | Fauzi M | DISCLOSED 2 | QUERIED 2 | Queried | OK | 0 | 0.024 | 0.024 |  | 310573 | 0 | 0 | 310573 | Fauzi M | PENDING PAYMENT | 1900-06-28
4 | KW-MSK-0524 | 62375 | MPIGI | BUWAMA | MBIZZINNYA | BUWAMA B | BUWA/AP019/018 | LO | KINALWA BENEDICTO (ADMINISTRATORS) |  |  | yes | yes |  | yes | N/A | 2 | 298 | MENGO-MAWOKOTA | Printed | Yes | 2 | 2017-06-20 | Yasir K. | DISCLOSED 2 | QUERIED 2 | Queried | OK | 0.0197 | 0.1677 | 0.1874 |  | 751696 | 0 | 0 | 751696 | Yasir K. | PENDING PAYMENT | 1900-06-28
5 | KW-MSK-0686 | 61255 | MPIGI | NKOZI | KAYABWE | KASUUBO | KASB/AP020/013 | LO | KAYABWE CATHOLIC CHURCH |  |  | yes | yes |  | yes | N/A |  |  |  | printed | Yes | 2 | 2014-06-26 | Joseph K | DISCLOSED 2 | QUERIED 2 | Queried | OK | 0.19 | 1.3069 | 1.4969 |  | 12937773 | 0 | 0 | 12937773 | Joseph K | PENDING PAYMENT | 1900-06-28 |  | No record of file upload; Folder missing
6 | KWD-MSK-SUP5-025 | 93942 | MPIGI | NKOZI |  | LUBANDA A | LUBA/AP025/942 | LO | LUTAAYA EMMANUEL, SSEMWANGA VINCENT & SSEMBATYA JOHN | 0754-388537/ 0752-538019 | CM79030102Q4TG/ CM40030102NK5K/ CM79030102TFWH | yes | yes | FILED | yes | N/A | 80 | 325 | MPIGI-MAWOKOTA | Printed | Yes | 2 |  |  | DISCLOSED 2 | QUERIED 2 | QUERIED |  | 0.117 | 0.813 | 0.93 |  | 20950020 | 0 | 0 | 20950020 |  | PENDING PAYMENT
7 | KWD-MSK-SUP5-026 | 93943 | MPIGI | NKOZI |  | LUBANDA A | LUBA/AP026/943 | LO | LUTAAYA EMMANUEL, SSEMWANGA VINCENT & SSEMBATYA JOHN | 0754-388537/ 0752-538019 | CM79030102Q4TG/ CM40030102NK5K/ CM79030102TFWH | yes | yes | FILED | yes | N | 79 | 325 | MPIGI-MAWOKOTA | Printed | Yes | 2 |  |  | DISCLOSED 2 | QUERIED 2 | QUERIED |  | 0.283 | 1.77 | 2.053 |  | 46382700 | 0 | 0 | 46382700 |  | PENDING PAYMENT
8 | KW-MSK-1023 | 55 | KALUNGU | LUKAYA TOWN COUNCIL | BAJJA WARD | BAJJA A | BAJA/AP025/002 | LO | WADDIMBA MICHAEL | 0759390287 |  | yes | yes |  | yes | N/A |  |  |  | Printed | Yes | 2 | 2014-10-29 | Fauzi M | DISCLOSED 2 | QUERIED 2 | QUERIED | OK | 0.1663 | 1.1614 | 1.3277 | 2019-05-13 | 6117714 | 0 | 0 | 6117714 | Fauzi M | PENDING PAYMENT | 1900-06-28
8 | KW-MSK-1023 | 60379 | KALUNGU | LUKAYA TOWN COUNCIL | BAJJA WARD | BAJJA A | BAJA/AP025/002 | LO | WADDIMBA MICHAEL | 0759390287 |  | yes | yes |  | yes | N/A |  |  |  | Printed | Yes | 2 | 2014-10-29 | Fauzi M | DISCLOSED 2 | QUERIED 2 | QUERIED | OK | 0.1663 | 1.1614 | 1.3277 | 2019-05-13 | 6117714 | 0 | 0 | 6117714 | Fauzi M | PENDING PAYMENT | 1900-06-28 |  | No record of file upload; Folder missing
8 | KW-MSK-1023 | 60380 | KALUNGU | LUKAYA TOWN COUNCIL | BAJJA WARD | BAJJA A | BAJA/AP025/002 | LO | WADDIMBA MICHAEL | 0759390287 |  | yes | yes |  | yes | N/A |  |  |  | Printed | Yes | 2 | 2014-10-29 | Fauzi M | DISCLOSED 2 | QUERIED 2 | QUERIED | OK | 0.1663 | 1.1614 | 1.3277 | 2019-05-13 | 6117714 | 0 | 0 | 6117714 | Fauzi M | PENDING PAYMENT | 1900-06-28 |  | 1 record of file upload; Folder missing
8 | KW-MSK-1023 | 62070 | KALUNGU | LUKAYA TOWN COUNCIL | BAJJA WARD | BAJJA A | BAJA/AP025/002 | LO | WADDIMBA MICHAEL | 0759390287 |  | yes | yes |  | yes | N/A |  |  |  | Printed | Yes | 2 | 2014-10-29 | Fauzi M | DISCLOSED 2 | QUERIED 2 | QUERIED | OK | 0.1663 | 1.1614 | 1.3277 | 2019-05-13 | 6117714 | 0 | 0 | 6117714 | Fauzi M | PENDING PAYMENT | 1900-06-28 |  | 1 record of file upload; Folder missing
9 | KW-MSK-1201 | 249 | KALUNGU | BUKULULA | KASAALI | KABALE | KABA/AP026/033 | LO | MWESIGWA FRED |  |  | yes | yes |  | yes | N/A |  |  |  | Printed | Yes | 2 |  | Wahab K. | DISCLOSED 2 | QUERIED 2 | Queried | OK | 0.1758 | 1.2944 | 1.4702 |  | 5073393 | 0 | 0 | 5073393 | Wahab K. | PENDING PAYMENT | 1900-06-28
10 | KMRS-0481 | 60240 | MASAKA | MUKUNGWE | KALAGALA | KITENGA B | KITE/AP028/016 | LO | SSEMWOGERERE GERALD MAJEERA |  |  | yes | yes |  | yes | N/A | 34 | 322 | MASAKA-BUDDU | Printed | Yes | 2 | 2013-09-25 | David M | DISCLOSED 2 | QUERIED 2 | QUERIED |  | 0.0351 | 0.2208 | 0.2559 |  | 2993015 | 0 | 0 | 2993015 | David M | PENDING PAYMENT | 1900-06-28 |  | No record of file upload; Folder missing
11 | KMRS-0514 |  | MASAKA | KATWE-BUTEGO | BUTEGO | KAMUGOMBWA- NAMASENENE | KANA/AP028/036 | T60 | NALUKWAGO SCOVIA | [7 empty] | N/A | N/A | N/A |  | Yes | 2 | 42542 | Wahab K. | DISCLOSED 2 | QUERIED 2 | Queried |  | 0 | 0.056 | 0.056 |  | 256689 | 806000 | 195000 | 1257689 | Wahab K. | PENDING PAYMENT | 1900-06-28
Files received by Audit so far
Note on Z1: Author: 7/2, 7/3 Skipped. Kasengejje, 9/4 Annita Gombe Skipped.
Note on B3: Author: KMRS-0096
Note on AB4: Author: Seach Shows caveat by Francson Kakoza SURVEY/VALUATION QUERY
Note on J5: Author: Was Limolo Mikidad. True owner was Ssenyonjo Mikidad who sold to Musoke Joseph
Note on AA5: Author: PAP Changed mind at payment depite of his original agreement on 14.04.2014
Note on AB5: Author: PAP rejected the cash. Refunded to PPA. 24.11.2014. file to the archive. File to the archive.
Note on J6: Author: Kayiwa Godfrey & Namale Maria Gorreti
Note on AB6: Author: One of the Admins. Sigend. The other PAP claims to come with the lawyer before consenting to the package. 04.05.2016. Rejected package. 20.06.2017
Note on J7: Author: had st mugaga kayabwe P/S
Note on AB7: Author: Fr. Mukiibi Leonard claims they have no tenant on the land
Note on J10: Author: transferred intrests to wadimba micheal who bought from mirundi who was the administrator to kibiina yowana
Note on AB10: Author: PAP dislolsed to and refused to sign and handing in his title. He needs the first tiltle with UETCL fisrt returned. 29.10.2014
Note on J11: Author: transferred intrests to wadimba micheal who bought from mirundi who was the administrator to kibiina yowana
Note on AB11: Author: PAP dislolsed to and refused to sign and handing in his title. He needs the first tiltle with UETCL fisrt returned. 29.10.2014
Note on J12: Author: transferred intrests to wadimba micheal who bought from mirundi who was the administrator to kibiina yowana
Note on AB12: Author: PAP dislolsed to and refused to sign and handing in his title. He needs the first tiltle with UETCL fisrt returned. 29.10.2014
Note on J13: Author: transferred intrests to wadimba micheal who bought from mirundi who was the administrator to kibiina yowana
Note on AB13: Author: PAP dislolsed to and refused to sign and handing in his title. He needs the first tiltle with UETCL fisrt returned. 29.10.2014
Note on AB14: Author: Need MD letter for disclosure. Cant sacrifice his title for 5m.
Note on B15: Author: KW(S)-MSK 096
Note on AB15: Author: Contacted but still needs more clarification. 27.07.2017
Note on J16: Author: NALONGO DEZI

## Files 2
NO. | NO. CONSULTANT'S | WIS HH_ID | DISTRICT | SUB - CTY | PARISH | Village/LC1 | PLOT REF. | DES | NAMES OF PAP | Survey/ Strip Map | Valuation/ Assessment | Soc Econ Info | STR /Fixture photos | Plot no. | Block no | Location | status | PAP photos | Option Grp (1, 2, 3A,3B) | DISCLOSURE STATUS | Remarks | STRINGING | ROW (acres) | WL (acres) | TOTAL Acreage | Re-disclosure Date | LAND ASSESSMENT | CROPS ASSESSMENT | STRUCTURES ASSESSMNT | FIXTURES ASSESSMENT | CULTURAL PROPERTY ASSESSMENT | TOTAL ASSESSMENT AMOUNT | INKIND LAND (ACRES) | INKIND RESETTLEMENT HOUSE | DISCLOSING OFFICER | Payment Status | INKIND DELIVERY (Land, House) | Comment
2 | 4KMRS-00002 | 76599 | WAKISO | WAKISO | NALUVULE | SENGE | SENG-AP007-145 | LO | PLOT 154 - BLOCK 260/261 |  |  |  |  | 154 | 260/261 | MENGO-BUSIRO | Not printed |  | 2 | UNDISCLOSED | ABSENTEE |  | 0.046 | 0.205 | 0.251 | [6 empty] | 65230961 | 0 |  |  | PENDING PAYMENT
3 | 4KMRS-00003 | 76600 | WAKISO | NABWERU | NALUVULE | SENGE | SENG-AP007-146 | LO | PLOT 155 - BLOCK 260/261 |  |  |  |  | 155 | 260/261 | MENGO-BUSIRO | Not printed |  | 2 | UNDISCLOSED | ABSENTEE |  | 0.05 | 0.195 | 0.245 | [6 empty] | 63840621 | 0 |  |  | PENDING PAYMENT
5 | 2KMRS-00014 | 76445 | WAKISO | WAKISO | NALUVULE | SENGE | SENG-MK008-140 | LO | PLOT 349 - BLOCK 260 |  |  |  |  | 349 | 260 | MENGO-BUSIRO |  |  | 2 | UNDISCLOSED | ABSENTEE |  |  |  | 0 | [6 empty] | 36681646 |  |  |  | PENDING PAYMENT
6 | 2KMRS-00042 | 75941 | WAKISO | WAKISO | NALUVULE | KAYUNGA | KYGA-AP009-008 | LO | BISASO FRANCIS | [6 empty] | MENGO-BUSIRO | Printed |  | 2 | UNDISCLOSED | Ready for disclosure |  | 0 |  | 0 | [6 empty] | 28026370 |  |  |  | PENDING PAYMENT
31 | GLT | 89204 | MPIGI | KIRINGENTE | KOLOLO | GALATIYA | GLTY-AP012-015 | LO | SSEBUKULU IBRAHIM | YES |  | MISSING | N/A | 160 | 507 | MPIGI-MAWOKOTA | Printed | MISSING | 2 | UNDISCLOSED | GALATIYA |  | 0.121 | 0.766 | 0.887 | [6 empty] | 172802500 | 0 | 0 |  | PENDING PAYMENT |  | No record of file upload; Folder missing
37 | GLT | 89211 | MPIGI | KIRINGENTE | KOLOLO | GALATIYA | GLTY-AP012-022 | LO | KAFUMA GEORGE & NAKUBULWA ELIZABETH | YES | YES |  | N/A | 330 | 507 | MPIGI-MAWOKOTA | Printed |  | 2 | UNDISCLOSED | GALATIYA |  | 0.08 | 0.59 | 0.67 |  | 43056000 |  |  |  |  | 43056000 | 0 | 0 |  | PENDING PAYMENT |  | 1 record of file upload; Folder missing
38 | GLT | 89214 | MPIGI | KIRINGENTE | KOLOLO | GALATIYA | GLTY-AP012-025 | LO | NSANJA RASHID | YES | YES | YES | N/A | 185 | 507 | MPIGI-MAWOKOTA | Printed |  | 2 | UNDISCLOSED | GALATIYA |  | 0.09 | 0.63 | 0.72 |  | 46332000 |  |  |  |  | 46332000 | 0 | 0 |  | PENDING PAYMENT |  | No record of file upload; Folder missing
42 | KW-MSK-0496 |  | MPIGI | KIRINGENTE | KAVULE | KIWAMIREMBE | KWMB-AP013-004 | LO | KABUUSU MUGWANYA GODFREY | [7 empty] | Not printed |  | 2 | UNDISCLOSED | LOA/NEK |  |  |  | 0 | [6 empty] | 93406123 |  |  |  | PENDING PAYMENT
44 | 2KMRS-00179 |  | MPIGI | KIRINGENTE | KAVULE | KYAMBIZZI | KYBZ-AP013-010 | LO | PLOT 44 - BLOCK 106 |  |  |  |  | 44 | 106 | MENGO-MAWOKOTA |  |  | 2 | UNDISCLOSED | ABSENTEE |  |  |  | 0 | [6 empty] | 35843317 |  |  |  | PENDING PAYMENT
51 | KW-MSK-0176 | 62319 | MPIGI | KAMENGO | KYANJA | NAMBI | NAMB/AP015/009 | LO | MUWAZI LOUIS | yes | yes | yes |  |  |  |  | Printed | Yes | 2 | UNDISCLOSED | LOA/NEK | OK |  |  | 0 | [6 empty] | 16931037 |  |  | 0 | PENDING PAYMENT |  | No record of file upload; Folder missing
52 | KW-MSK-0191 | 60868 | MPIGI | KAMENGO | KYANJA | NAMBI | NAMB/AP015/011 | LO | MUWAZI LOUIS | yes | yes | yes |  |  |  |  | Printed | Yes | 2 | UNDISCLOSED | LOA/NEK | OK |  |  | 0 | [6 empty] | 10691590 |  |  | 0 | PENDING PAYMENT |  | No record of file upload; Folder missing
55 | KW-MSK-0218 |  | MPIGI | KAMENGO | KYANJA | KWAABA KABIRA | KWKA/AP016/003 | T5 | BUGANDA LAND BOARD |  |  |  |  | N/A | N/A | N/A | Not Printed |  | 2 | UNDISCLOSED | Title issues | OK | 0.323 | 2.265 | 2.588 | [6 empty] | 7453651 |  |  | 0 | PENDING PAYMENT
62 | KMRS-0228 |  | MPIGI | BUDDE | SABADDU | KABUYE-NTAYI | KANT/AP017/011 | LO | BUGANDA LAND BOARD | LANDLORD | [8 empty] | 2 | UNDISCLOSED | Title issues |  |  |  | 0 | [6 empty] | 13279725 |  |  |  | PENDING PAYMENT
79 | 2KMRS-00277 |  | MPIGI | NKOZI | MUGGE | LWABITEETE | LWAB/AP022/015 | LO | BUYINZA FAMILY (MINORS) |  |  |  |  | 74 | 415 | MENGO-MAWOKOTA | Not Printed |  | 2 | UNDISCLOSED | Title issues | [10 empty] | 71240000 |  |  |  | PENDING PAYMENT
87 | KW-MSK-1123 |  | KALUNGU | BUKULULA | MUKOKO | KISANJE WEST | KISW/AP026/006 | T7 | SEMAKULA SPACIOZA NAKAKAWA | yes | yes | no |  | N/A | N/A | N/A | Not Printed |  | 2 | UNDISCLOSED | Ownership dispute | OK |  |  | 0 | [6 empty] | 3599994 |  |  | 0 | PENDING PAYMENT
93 | KW-MSK-1293 |  | MASAKA | MUKUNGWE | MATANGA | KADDUGALA -NSANGAMO | KANS/AP027/016 | LO | BUGANDA LAND BOARD | no | yes | N/A |  |  |  |  | Not Printed |  | 2 | UNDISCLOSED | Title issues | OK | 0.536 | 3.788 | 4.324 | [6 empty] | 24897191 |  |  | 0 | PENDING PAYMENT
94 | KW-MSK-1306 |  | MASAKA | MUKUNGWE | MATANGA | KADDUGALA -NSANGAMO | KANS/AP027/018 | LO | BUGANDA LAND BOARD | no | yes | N/A |  |  |  |  | Not Printed |  | 2 | UNDISCLOSED | Title issues | OK | 0.093 | 0.654 | 0.747 | [6 empty] | 14358521 |  |  | 0 | PENDING PAYMENT
95 | KMRS-0461 | 73462 | MASAKA | MUKUNGWE | SAMALIYA | BUTAALE | BUTA/AP027/025 | LO | BUGANDA LANDBOARD | LANDLORD | [6 empty] | Printed |  | 2 | UNDISCLOSED | Title issues | OK |  |  | 0 | [6 empty] | 20580838 |  |  |  | PENDING PAYMENT |  | No record of file upload; Folder missing
97 | KW-MSK-1468 |  | MASAKA | KATWE-BUTENGO DIV | BUTENGO | KALAGALA-KITEREDDE | KAKI/AP028/031 | LO | BUGANDA LAND BOARD | no | no | no |  |  |  |  | Not Printed |  | 2 | UNDISCLOSED | Title issues |  | 0.456 | 3.288 | 3.744 | [6 empty] | 32313885 |  |  | 0 | PENDING PAYMENT
98 | KW-MSK-1485 |  | MASAKA | KATWE-BUTENGO DIV | BUTENGO | KALAGALA-KITEREDDE | KAKI/AP028/033 | LO | BUGANDA LAND BOARD | [7 empty] | Not Printed |  | 2 | UNDISCLOSED | Title issues |  | 0.551 | 3.804 | 4.355 | [6 empty] | 37641677 |  |  | 0 | PENDING PAYMENT
99 | KMRS-0513 | 62269 | MASAKA | KATWE-BUTENGO DIV | BUTENGO | KAMUGOMBWA- NAMASENENE | KANA/AP028/035 | T33 | MAWEJJE DEOGRATIUS | yes | yes | yes | N/A | N/A | N/A | N/A | Printed | Yes | 2 | UNDISCLOSED | Ownership dispute |  | 0.0026 | 0.0686 | 0.0712 | 2015-11-09 | 3240379 | 1076400 | 21125000 | 234000 |  | 25675779 | 0 | 0 | Wahab K. | PENDING PAYMENT
100 | 2KMRS-00327 | 62269 | MASAKA | KATWE-BUTENGO DIV | BUTENGO | KAMUGOMBWA- NAMASENENE | KANA/AP028/035 | L1 | MAWEJJE DEOGRATIUS | N/A | [6 empty] | Printed |  | 1 | UNDISCLOSED | Ownership dispute |  | 0 | 0 | 0 |  | 0 | 1076400 | 0 | 0 | 0 | 1076400 | 0 | 0 |  | PENDING PAYMENT
Note on B2: Author: KMRS-0008 & 2KMRS-00008
Note on B3: Author: KMRS-0009 & 2KMRS-00009
Note on V9: Author: UETCL
Note on J10: Author: Title in Sebanakitta's names. Submitted wrong title.
Note on V11: Author: UETCL
Note on V12: Author: UETCL
Note on B14: Author: KW-MSK-0344
Note on H14: Author: 002-LO
Note on J16: Author: clarity needed from family/c/man
Note on B22: Author: KW-MSK-1539
Note on J22: Author: Deceased but there are two contesting parties.
Note on M22: Author: Not endorsed by PAP, FO and PLC
Note on V22: Author: Deceased but PPO(SA) recommends a GRC process. With GR team 26.07.2019 26.07.2019. PAP claims it's only land and ecalyptus affected. Structures not his.